## Compliance Checklist
BENEDICT'S LAW (2026) — SCHOOL COMPLIANCE TRACKER
Actionable checklist and progress dashboard to prepare your school for statutory compliance before September 2026
SCHOOL METADATA & COMPLIANCE TARGETS |  |  |  | OVERALL PROGRESS DASHBOARD
School Name: | Enter your school's name here |  |  | Total Compliance Tasks: |  | 18
School Sector: | State Sector / Academy |  |  | Tasks Not Started: |  | 17
Compliance Deadline: | End of Autumn Term 2026 (Dec 31, 2026) |  |  | Tasks In Progress: |  | 1
SLT Allergy Safety Lead: | Appoint SLT Lead (Immediate action) |  |  | Tasks Completed: |  | 0
|  |  |  | Overall Compliance Rate: |  | 0%
Pillar ID | Pillar Name | Required Compliance Task | Assigned Owner | Target Date | Status | Legal Compliance Notes & References
1.1 | 1. Standalone Allergy Policy | Appoint Senior Leadership Team (SLT) lead for allergy safety. | Head Teacher / SLT | Immediate | In Progress | Benedict's Law requires an SLT lead to oversee allergy compliance and near-miss logs [6,7].
1.2 |  | Separate allergy protocols from generic 'Supporting Pupils with Medical Conditions' document. | SLT Lead | Before Sept 2026 | Not Started | Must be a dedicated, standalone Allergy Policy. Annual review is mandatory [4,7].
1.3 |  | Publish the standalone Allergy Policy on the school's public website. | Office / IT Team | Before Sept 2026 | Not Started | Statutory requirement to have the policy accessible on the public school website [4,7].
1.4 |  | Incorporate clear risk mitigation strategies and emergency response workflows in policy. | SLT Lead / Chef | Before Sept 2026 | Not Started | Must explicitly outline emergency workflows and food safety checks [4].
2.1 | 2. Whole-Staff Training | Audit all school-associated staff to create a master training list. | SLT Lead | Immediate | Not Started | Includes teachers, TAs, catering, admin, caretaking, cleaning, drivers, and club leaders [5].
2.2 |  | Coordinate a 1-hour accredited training block for all identified staff. | SLT Lead / HR | Autumn Term 2026 | Not Started | Training must be completed during Autumn Term 2026 (Spring 2027 for independent settings) [7,8].
2.3 |  | Roll out free, DfE-endorsed training modules via Natasha's Foundation 'Allergy School'. | All Staff | Autumn Term 2026 | Not Started | DfE-endorsed training from Allergy School is accredited and 100% free [7].
2.4 |  | Verify and log completion certificates for all staff to maintain an audit trail. | HR / Office | Autumn Term 2026 | Not Started | Audit-ready training logs must be securely stored and kept up-to-date [7,9].
3.1 | 3. Spare Emergency AAIs | Audit the physical layout of school premises to map optimal AAI storage. | SLT Lead / Nurse | Immediate | Not Started | AAIs must be physically reachable and adminsterable within 5 minutes of any reaction [5,7].
3.2 |  | Calculate the quantity of unprescribed, spare AAIs needed for full coverage. | SLT Lead / Nurse | Before Sept 2026 | Not Started | Consider classrooms, sports fields, playgrounds, and halls to meet 5-minute requirement [5,7].
3.3 |  | Procure backup stock of spare AAIs (EpiPens/Jext) from a trusted medical supplier. | School Business Mgr | Before Sept 2026 | Not Started | Required to safeguard pupils with expired/broken devices or first-time reactions [5,7].
3.4 |  | Create a weekly check roster for checking spare AAI expiry dates and status. | School Nurse | Weekly | Not Started | Ensures backup devices are always active and in-date [5].
4.1 | 4. Individual Healthcare Plans | Compile a register of all students with allergies based on parental reports. | School Nurse / Admin | Immediate | Not Started | Parental report is sufficient to trigger a plan — formal clinical diagnosis is NOT required [6].
4.2 |  | Draft or meticulously update Individual Healthcare Plans (IHPs) / Allergy Action Plans. | School Nurse / SLT | Before Sept 2026 | Not Started | Every student with an allergy must have an updated IHP in place before term starts [6,7].
4.3 |  | Secure formal parental sign-off for each completed IHP. | School Nurse / SLT | Before Sept 2026 | Not Started | Essential safeguarding step before the pupil begins the school year [7].
5.1 | 5. Inclusion & Reporting | Map out safe and inclusive plans for trips, school meals, and celebrations. | SLT / Catering Lead | Before Sept 2026 | Not Started | The law targets the social impact of allergies; children must not be isolated [6].
5.2 |  | Establish a formal, digital log for tracking all allergy near-misses and incidents. | SLT Lead | Immediate | Not Started | Near-miss logs (like Kitchen OS Food Safe System) prevent future safety lapses [6,9].
5.3 |  | Implement a monthly SLT review cycle for logged allergy incidents. | SLT Lead | Monthly | Not Started | The appointed SLT lead must review logs regularly to refine school safety [6].